## QA-estimation-details
QA Estimation
Test Preparation | [5 empty] | Test Execution |  |  |  | Comment |  |  |  | Sub-modulewise
Modules | Sub-Modules | Total Test Cases | Estimated time (in man days) | Requirement analysis and share understanding(in man days) | Data preparation | Total browsers | Test Cycles | Test cases | Estimated time (in man days) | [5 empty] | design & execution effort | Design & execution ratio | Review & bug fixing effort | effort
Login | Login Page | 7 | 0.21875 |  | 0.058333 | 1 | 1 | 7 | 0.11667 |  |  |  | DE effort | 0.1125 | 0.39375 | 3.5 | 26.1333 | 26.5271
Dashboard | Navigation Bar | 4 | 0.125 |  | 0.033333 | 1 | 1 | 4 | 0.066667
| DRIVER | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  |  |  | RB effort | 7.4667 | 0.05625 | 0.5 | 3.7333 | 3.7896
| Black Spots by Severity | 5 | 0.15625 |  | 0.041667 | 1 | 1 | 5 | 0.083333 | [5 empty] | 0.28125 | 2.5 | 18.6667 | 18.9479
| Incidents: Last Two Weeks map | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 | [5 empty] | 0.16875 | 1.5 | 11.2 | 11.3688
| Total economic loss and societal harm: Last 90 days | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 |  | BJIT SQA Productivity |  |  |  | 0.1125 | 1 | 7.4667 | 7.5792
| Number of incidents | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 |  | Task | Time(min) |  |  | 0.16875 | 1.5 | 11.2 | 11.3688
| Time of Day, Day of Week: Last 90 Days | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 |  | Test case preparation | 15 |  |  | 0.16875 | 1.5 | 11.2 | 11.3688
| Saved Filters | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 |  | Test execution | 8 |  |  | 0.16875 | 1.5 | 11.2 | 11.3688
My Account | Account Information | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 |  | Bug report | 10 |  |  | 0.1125 | 1 | 7.4667 | 7.5792
Manage Duplicate Records | Potential Duplicate Records | 4 | 0.125 |  | 0.033333 | 1 | 1 | 4 | 0.066667 |  | Bug retest | 15 |  |  | 0.225 | 2 | 14.9333 | 15.1583
Map | Filter type | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 |  | Review test case | 5 |  |  | 0.16875 | 1.5 | 11.2 | 11.3688
| Control Layer Toggle | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 |  | Data Preparation | 4 |  |  | 0.16875 | 1.5 | 11.2 | 11.3688
| Zoom in & zoom out icon | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 1 | 7.4667 | 7.5792
| Zoom to | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 1 | 7.4667 | 7.5792
| Draw a polygon | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 1 | 7.4667 | 7.5792
| Draw a rectangle | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 1 | 7.4667 | 7.5792
| Layer Edit | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 1 | 7.4667 | 7.5792
| Layer Delete | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 1 | 7.4667 | 7.5792
| Footer | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 | [5 empty] | 0.16875 | 1.5 | 11.2 | 11.3688
| Graphs | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 1 | 7.4667 | 7.5792
| Export > Custom report | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 | [5 empty] | 0.16875 | 1.5 | 11.2 | 11.3688
| Export > Export CSV | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 |  |  |  |  | Ttl | 3.3188 | 29.5 | 220.2667 | 223.5854
| Traffic Enforcement Assignments | 6 | 0.1875 |  | 0.05 | 1 | 1 | 6 | 0.1
| Loss amount (Pop-up view) | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333
Record List | Filter Bar | 4 | 0.125 |  | 0.033333 | 1 | 1 | 4 | 0.066667
| Occured Date > From date | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333
| Occured Date > To Date | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333
| Weather | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667
| Saved Filters | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333
| Clear Filters | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667
| Add a record | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333
| View | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667
| Edit | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667
Add a record | Incident Location | 4 | 0.125 |  | 0.033333 | 1 | 1 | 4 | 0.066667
| Incident Time | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05
| RCF (Road Crash Form) | 7 | 0.21875 |  | 0.058333 | 1 | 1 | 7 | 0.11667
| ARF (Accident Report Form) | 7 | 0.21875 |  | 0.058333 | 1 | 1 | 7 | 0.11667
Total |  | 110 | 3.4375 | 0 | 0.91667 |  |  | 110 | 1.8333
Test Management | Test Case Review | 110 | 1.1458
| Scrum, Meeting and Reporting | 0 | 0 | [5 empty] | 0
| Bug Reporting (considering 20% bug) | 20 | 0 |  |  |  |  | 22 | 0.45833
| Bug Retesting (20% bug) | 0 | 0 |  |  |  |  | 22 | 0.6875
| Regression Testing (considering 25% of total test cases) | 0 | 0 |  |  |  |  | 0 | 0
| Integration Testing | 0 | 0 |  |  |  |  | 0 | 0
| BAT | 0 | 0 |  |  |  |  | 0 | 0
| Basic Testing on others devices (25%) | 0 | 0 |  |  |  |  | 0 | 0
|  | Test Preparation (Total Man Day): |  |  | 4.6 | Test Execution, Bug Reporting and Retesting Time (Total Man Day): |  |  | 2.9792
[7 empty] | Total Effort (man-day) |  | 7.5792
[7 empty] | Total Effort (man-month) |  | 0.37896
| SQA Velocity |  |  |  | Note:
| Task |  | Execution per man day |  | 1 Add notes
| Test case design productivity |  | 32 |  | 2
| Test case execution productivity |  | 60 |  | 3
| Test case review |  | 96 |  | 4
5

## assumptions
# | Assumptions/Restrictions
1
2
3
4
5
6
7
8

## RAP
# | Res | Rank | Tech group | Unit price | Sep | Oct | Nov | Total cost
1 | BSE | 8 | 4 |  |  |  |  | 0
2 | PM | 6 | 4 |  |  |  |  | 0
3 | Front-1 | 5 | 4 |  |  |  |  | 0
4 | Front-2 | 4 | 4 |  |  |  |  | 0
5 | Back-1 | 5 | 4 |  |  |  |  | 0
6 | Back-2 | 4 | 4 |  |  |  |  | 0
7 | Back-3 | 4 | 4 |  |  |  |  | 0
9 | UX Designer | 5 | 4 |  |  |  |  | 0
10 | QA-1 | 5 | 4 |  |  |  |  | 0
11 | QA-2 | 4 | 4 |  |  |  |  | 0
| Total |  |  |  | 0 | 0 | 0 | 0

## estimation-summary
# | Module/Feature/Screen | Requirement Analysis (man-day) | UX Design (man-day) | API spec prep (man-day) | UI Development (man-day) | Backend Development (man-day) | Testing (man-day) | Total (man-day) | Common Tasks | Efforts (man day)
1-1 | Login | [6 empty] | 0
1-2 | [7 empty] | 0
1-3 | [7 empty] | 0
1-4 | [7 empty] | 0 | Total (Man Day): | 0
1-5 | [7 empty] | 0 | Total (Man Month): | 0
1-6 | [7 empty] | 0 | Grant-Total (Man Month): | 0
1-7 | [7 empty] | 0
2 | [7 empty] | 0
3-1 | [7 empty] | 0
3-2 | [7 empty] | 0
4-1 | [7 empty] | 0
4-2 | [7 empty] | 0
5-1&2 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
0
0
| Total (Man Day): | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (Man Month): | 0 | 0 | 0 | 0 | 0 | 0 | 0

## estimation-detail
# | Modules | Features/ Screens | Related Feature ID/Screen No | Tasks | Requirement Analysis | UX Design | API spec preparation | Frontend Development (Man Day) |  |  |  | Backend Development (Man Day) |  |  | Development Total (Man Day) | Common tasks (Man Day) | Total (Man Day)
[8 empty] | UI Design | Function Integration & UI Validation | Internal Review & UI Bug fixing | Total | Function Implementation | Internal Review & Issue fixing | Total
Project Name | Screens | [9 empty] | 0 |  |  | 0 | 0 |  | 0
[11 empty] | 0 |  |  | 0 | 0 |  | 0
[11 empty] | 0 |  |  | 0 | 0 |  | 0
[11 empty] | 0 |  |  | 0 | 0 |  | 0
[11 empty] | 0 |  |  | 0 | 0 |  | 0
[11 empty] | 0 |  |  | 0 | 0 |  | 0
[11 empty] | 0 |  |  | 0 | 0 |  | 0
| Common | [9 empty] | 0 |  |  | 0 | 0 |  | 0
[14 empty] | 6 | 6 |  | 6
[14 empty] | 5 | 5 |  | 5
[14 empty] | 5 | 5 |  | 5
Common tasks
|  |  |  | Total (Man Day): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 16
|  |  |  | Total (Man Month): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0.8 | 0 | 0.8

## browser-compatibility
Supported Environments and Browsers
Device | OS | OS Version | Browser | Coverage | Comment
PC | Mac OS | 10.14/latest OS | Google Chrome (Latest Version) | 1
|  |  | Safari (Latest Version) | 1
| Windows | 10 | Google Chrome (Latest Version) | 1
|  |  | Microsoft Edge (Latest Version) | 0
|  |  | Internet Explorer 11 | 0
|  |  | Safari (Latest Version) | 0
|  |  | Firefox (Latest Version) | 1
SP | iOS | 12.4/latest | Google Chrome (Latest Version) | 0
|  | 12.4/latest | Safari (Latest Version) | 1 | Only 1 device (latest)
| Android | 10/latest | Google Chrome (Latest Version) | 1 | Only 1 device from Samsung (latest)
Tab/iPad | iPad | 12.4/latest | Google Chrome (Latest Version) | 0
|  | 12.4/latest | Safari (Latest Version) | 1 | Only 1 device (latest)
| Tab | 10/latest | Google Chrome (Latest Version) | 1 | Only 1 device from Samsung (latest)
Total: |  |  |  | 8