## Cover
QA Report
Sprint | : | 1
Project | : | DRIVER
Build | : | V-1.0.0
Date | : | 2023-09-27
Reporter | : | Rana Tabassum

## Release Summary
DRIVER Release Summary Report
Release Info |  | Browser & Device List
Release Name | 1.0.0 | # | Desktop web Browser | Version
Version Name | 1.0.0 | 1 | PC (Windows) | Win-11
Release Topic | Login Dashboard Manage Duplicate Records My Account Map Record List Add a record
|  | 2 | Chrome | Version 116.0.5845.188
Start Date | 25.09.2023
End Date | 27.09.2023
QA Release Date | 27.09.2024
Release Status | N/A
Released By | Rana Tabassum
Prepared By | Rana Tabassum
Verified By | Abdul Qadir
Executed Test Type:
1 | Functional test
2 | UI test
3 | System testing
Non Executed Test Type:
1 | Regression
2 | Security
3 | Retesting
4 | Pixel perfection testing
5 | Scope testing
6 | Non-functional testing
7 | Device compatibility
8 | Hardware failure
9 | User Acceptance Testing

## Functionality Verification
DRIVER Release Checklist
# | Module | TL Confirmation | Verified by QA | Status (by QA) | TL Comment | QA Comment
1 | Login | Yes | Yes | OK
2 | Dashboard | Yes | Yes | NG |  | Task #479808 , Task #479813
3 | Manage Duplicate Records | Yes | Yes | NG |  | Task #479837
4 | My Account | Yes | Yes | OK
5 | Map | Yes | Yes | NG |  | Task #479842
6 | Record List | Yes | Yes | NG |  | Task #479842
7 | Add a record | Yes | Yes | NG |  | Task #479838
[N.B: We have checked all screens and found some major and minor issues, these are posted in Jira]

## Graphical Report
Test Case Execution Report
| Build Version No: | V-1.0.0
| Total Test cases: | 120
| Test Environments (Browsers): | 1
| Total Executable test cases: | 120
| Test Cases Executed: | 115
| Passed: | 108
| Failed: | 7
| NA: | 5
| WIP: | 0
| Total Reported Bugs : | 7
| New | 0
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 6
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Immediate : | 0
| Urgent : | 0
| High: | 1
| Normal: | 0
| Low: | 6
| Total: | 7
| Reported Bugs : (All Sprints) | 7
| New | 7
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Low | 2
| Medium | 21
| High | 98
| Urgent | 0
| Immediate | 0
| Total: | 121
Step-2: Full Bug summary
Total Bugs (Priority wise):
Total Bug summary
Total Bugs (Priority wise):

## Bug_list
Sprint#1 Bug List
Bug Type | Quantity
UI: | 0
Functional: | 7
Total: | 7
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | _ | _ | _ | _ | Minor
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | B_01 | In the dashboard, Incidents in the Last Two Weeks section Is not displaying the blue dots on the Map | New | Normal | Minor
2 | B_02 | In the dashboard, Clicking on "View all incidents" from the "Incidents: Last Two Weeks" section does not display the expected result of all incidents from last two weeks | New | Low | Minor
3 | B_03 | Users are not redirected to the "Potential Duplicate Records" page when clicking on "Manage Duplicate Records." | New | Low | Minor
4 | B_04 | System does not allow Saving Record with Present Time that is Already Generated While Opening the Form and doesn't even show any error message before attempting to save the record. | New | High | Minor
5 | B_05 | Unable to Delete Uploaded Location Sketch In the RCF Form | New | Low | Minor
6 | B_06 | Filter bar allows future date in “To” section of the occurred date filter. | New | Low | Minor
7 | B_07 | Filter bar allows future date in "From" section of the occurred date filter. | New | Low | Minor
Functional Bugs:
Step-2: Sprint#3- Bug summary
UI Bugs:

## Bug_trend
Sprint | Test case | Bugs | Resolved | Trend
V-1.0.0 | 120 | 7 | 0 | 0

## Defect density
Sprint | Effort | Defect | Defect density | Defect density
V-1.0.0 | 0 | 0 | #DIV/0! | #DIV/0!